## Sheet1
Graded Milestones |  | Status |  | FILE | OWNER | DUE | STATUS | NOTES
2007-05-08 | Group Presentation
2007-04-26 | IPR 3 Completed |  |  | Outline Use Cases | McBride | 2007-02-08 | Completed
2007-03-29 | IPR 2 Completed
2007-02-23 | Database Built |  |  | Outline Database (UML Diagram) | Jensen | 2007-02-08 | Completed
2007-02-08 | IPR 1 complete
2007-01-25 | Problem Spec due |  |  | Outline Webpage Map & Design | Merz, Horn | 2007-02-08 | Completed
Group Meetings | Time |  | Focus | Build Database Tables | Merz | 2007-02-20 | < 50% Complete | Database Due 23 Feb
2007-05-07 | 2000 |  | Presentation Prep
2007-04-25 | 2000 |  | IPR 3 Prep | Populate Tables with Data | Jensen | 2007-02-20 | < 50% Complete | Database Due 23 Feb
2007-04-11 | 2000 |  | Code/Debugging
2007-03-28 | 2000 |  | IPR 2 Prep | Create database relationships and foreign keys | Horn | 2007-02-21 | < 50% Complete | Database Due 23 Feb
2007-03-21 | 2000 |  | Post Break Refocus
2007-03-07 | 2000 |  | Webpage Implementation | Complete Database and debug | Mcbride | 2007-02-23 | < 50% Complete | Database Due 23 Feb
2007-02-21 | 2130 |  | Database Turn-In prep
|  |  |  | Complete Webpage Template | Merz | 2007-03-01 | 51-99% Complete
Client IPRs | Time |  |  | Login Page | Merz | 2007-03-04 | < 50% Complete
2007-02-22 | 745
2007-03-28 | 745 |  |  | Login Script | Merz | 2007-03-04 | < 50% Complete
|  |  |  | Equipment Search Page | Horn | 2007-03-26 | < 50% Complete
|  |  |  | Equipment Search Script | Horn | 2007-03-26 | < 50% Complete
|  |  |  | Equipment Search Queries | Horn | 2007-03-26 | < 50% Complete
|  |  |  | Check out/in page | McBride | 2007-03-26 | < 50% Complete
|  |  |  | Check out script | McBride | 2007-03-26 | < 50% Complete
|  |  |  | Check in Script | McBride | 2007-03-26 | < 50% Complete
|  |  |  | Add/Delete User Page | Jensen | 2007-03-26 | < 50% Complete
|  |  |  | Add/Delete Script | Jensen | 2007-03-26 | < 50% Complete
|  |  |  | Reservations Page | Merz | 2007-03-28 | < 50% Complete | IPR 2 on 29 Mar
|  |  |  | Search reservation script | Merz | 2007-03-28 | < 50% Complete
|  |  |  | Make reservation script | merz | 2007-03-28 | < 50% Complete
|  |  |  | Cancel reservation script | Merz | 2007-03-28 | < 50% Complete
|  |  |  | State Management | McBride | 2007-04-24 | < 50% Complete
|  |  |  | Subclass Implementation | Horn | 2007-05-04 | < 50% Complete
|  |  |  | Basic Client Side Implementation | Merz | 2007-05-04 | < 50% Complete
|  |  |  | Advanced Client Side Verification | Jensen | 2007-05-04 | < 50% Complete
|  |  |  | Final Debug | Team | 2007-05-05 | < 50% Complete
|  |  |  | Final Implementation | Team | 2007-05-07 | < 50% Complete